## Enterprise Bus Matrix
Grain | Drug | DrugItem | Manufacturer | DrugItemPackage | Prescription | Client Health-Care Organization | Pharmacist | OrderItem | Order | ClientUnit | Patient | Dimension Usage Count | Complexity | Grain Estimates | Analysis | Modeling | Source Target Mapping | Build & Unit Test | Estimate
Daerah dengan Pembelian Tertinggi |  |  |  |  | x | x | x | x | x | x | x | 7 | C |  | 1.2 | 1.2 | 1.2 | 4.4 | 8
Jenis Kelamin yang paling sering ke Apotik (Sudah Membeli) |  |  |  |  | x |  | x | x | x |  | x | 5 | M |  | 0.75 | 0.75 | 0.75 | 2.75 | 5
Total Pembelian untuk setiap produk |  | x |  | x | x |  | x | x | x |  | x | 7 | C |  | 1.2 | 1.2 | 1.2 | 4.4 | 8
Grain Usage Count | 0 | 1 | 0 | 1 | 3 | 1 | 3 | 3 | 3 | 1 | 3 |  |  |  | 3.15 | 3.15 | 3.15 | 11.55 | 21
Complexity | S | C | S | C | C | S | M | C | C | S | S
Estimates
Analysis | 0.45 | 1.2 | 0.45 | 1.2 | 1.2 | 0.45 | 0.75 | 1.2 | 1.2 | 0.45 | 0.45 | 9 |  |  |  |  | Total Days | 81
Modeling | 0.45 | 1.2 | 0.45 | 1.2 | 1.2 | 0.45 | 0.75 | 1.2 | 1.2 | 0.45 | 0.45 | 9
Source Target Mapping | 0.45 | 1.2 | 0.45 | 1.2 | 1.2 | 0.45 | 0.75 | 1.2 | 1.2 | 0.45 | 0.45 | 9
Build & Unit Test | 1.65 | 4.4 | 1.65 | 4.4 | 4.4 | 1.65 | 2.75 | 4.4 | 4.4 | 1.65 | 1.65 | 33
Estimate | 3 | 8 | 3 | 8 | 8 | 3 | 5 | 8 | 8 | 3 | 3 | 60

## Project Work Breakdown
Work Breakdown | Price Details
| Days | Rate | $ | Notes
Analysis
Business Analysis | 4 | 1200 | 4800 | Investigate requirements, business processes, sources.
High Level Design | 2 | 1200 | 2400 | Develop a high level design for the DW.
PreRequisites
Establish Development Environment | 2 | 1200 | 2400
Establish Test Environment | 1 | 1200 | 1200
Build and Unit Test
Data Warehouse | 60 | 1200 | 72000
Dimensions | 21 | 1200 | 25200
Facts | 11 | 1200 | 13200
Cube/Tablular Model | 4 | 1200 | 4800 | Including any calculated Measures
Master Data (Reference Data) | 5 | 1200 | 6000 | Setup Master Data.
System/UAT Testing | 5 | 1200 | 6000 | This represents time required to respond to issues found in Testing
Deployment | 2 | 1200 | 2400 | Several Deployments over course of project, including TEST and PROD.
Security | 5 | 1200 | 6000 | Implement data security.
Project Management | 3 | 1200 | 3600 | Time for reporting status, communication, management.
Documentation & Handover |  |  |  | Solution documentation and handover.
Total Day/$ | 125 |  | 150000

## Complexity Details
Estimates
The table below to assign a number of days to each of the complexity options available in the Data Warehouse matrix.
Complexity Code | Complexity Name | Estimate (Days) | Fact Estimate (Days) | Description
S | Simple | 1 | 3 | A Simple Dimension or Fact is source from a single existing source, with mostly a one to one relationship between source columns and destination columns. The Source is readily available and accessible.
M | Medium | 1.75 | 5 | A Medium Dimension or Fact is source from a single existing source, with mostly a one to one relationship between source columns and destination columns. However the source many need to be created, purely for reporting purposes, or there may be many attributes or measures.
C | Complex | 2.8 | 8 | Complex will involves at least one issues like: the Source is undecided, data quality issues, multiple sources, many attributes, many measures, many dimension associations, or there are complex transformations and/or derived staging tables required to derive measures or attributes.
HC | Highly Complex | 4.2 | 12 | Highly Complex will involve a combination of a number of issues like: the Source is undecided, data quality issues, multiple sources, many attributes, many measures, many dimension associations, or there are complex transformations and/or derived staging tables required to derive measures or attributes.
Task Breakdown
The table below to breakdown the work required for each Fact and Dimension into Analysis, Modelling, Source-Target mapping and Build/Unit Testing tasks. The breakdown is used in the Data Warehouse Matrix spreadsheet to break down all work over these task categories.
Task | Breakdown
Analysis | 15%
Modeling | 15%
Source Target Mapping | 15%
Build & Unit Test, Integrate | 55%
Variables
Daily Rate | 1200
Note on C22: agilmore: Set the daily rate of labour on the project This is isn't just annual salary/number of work days in a year (approx 200). This usually includes an overhead for providing the workplace and all other costs associated with employment.